## Sheet1
Date | Duration | Type | Work Perfromed | Challenges | Next Steps?
Week 1
2023-01-26 | 1hr | orientation | attended orientation |  | Perfrom research and draft ideas for project
2023-01-27 | 2hr | research & file set up | research how to implement Javascript Google Map Api |  | Navigating Google Maps Platform and finding proper documentation for project. Set up file system.
2023-01-28 | 2.5hr | research | find webpages implemented with Google Map Api |  | design page layout
2023-01-29
Goals: get a general idea of how I'd like to set up webpage
Week 2
2023-01-30 | 4hr | design | began implementing divs, background colors, of html |  | further develop css
2023-01-31 | 3hr | design | implemented map onto page, created header and header text | understanding how to use Google Map API calling function onto page | size map onto page and do more css implementatino
2023-02-01
2023-02-02 | 1.5hr | Supervisor Meeting | Spoke on desires of webpage and implement logging method |  | fill project report
2023-02-03 | 2.5hr | filing project report | sat with supervisor to speak about goals and filled out report together |  | readability & scalability of webpage
2023-02-04 |  | coding | Added functionality, methods, and notes onto js files | trying to understand how to get user's current location | add mock data onto page
2023-02-05
goals: continue to develop web page to find desired page flow. Challenges: being able to receive feedback from my supervisor was tough. He wanted to see more progress than I already had.
Week 3
2023-02-06 | 2hr | design | reformatted design to hold list items of attratctions on map and images | formatting page to properly hold the elemnts of the page | fill out lists with conent
2023-02-07 | 2hr | research | researched examples of how people organize info on sites, how to display content |  | fill out lists with conent
2023-02-08 | 1.5hr | research | found viable idea for carousel to move through images |  | fill out lists with conent
2023-02-09
2023-02-10 | 2hr | coding | implement carousel into project coding | i got the images formatted into the box but the picture is pixilated | fix image resolution
2023-02-11 | 1hr | research | Gave myself authorized use for all Google Maps API utilities | Navigating the site is difficult!
2023-02-12 | 1hr | research | Trying to figure out how to get data from map onto carousel image | having trouble accessing the properties of results
2023-02-13 | 2hr | documentation | document my time from this and last week
Goals: Dive deep into code to move map information onto lists Challenges: working with a new complex Api like this is harder than I thought
Week 4
2023-02-14 | 3hr | back work | figured out chrome inspect can show screen sizes and saw my lay out was terrible so i changed everything to fit large screen size | having to move everything took time and hard to fnd layout suitable for initial design | determine next steps
2023-02-15 | 2hr | research | refreshed my memory on how Yelp Api functioned and looked at past examples |  | think about how to add Yelp to site
2023-02-16 | 3.5hr | implementation | saw markers were a good idea to add to map and worked on getting it onto page | Had trouble getting current location to be applied to map, kept getting error that it couldn't retrieve current position in time | Figure out markers on current location
2023-02-17 | 2hr | coding | markers was a go for result location in query serach. Still can't get current position working | figuring out the properties of the results was hard but after looking at console, things were laid out | decide if i wanna keep current location
2023-02-18
2023-02-19 | 1hr | coding | stop focuising on current location functionality, I couldn't figure it out so I'll hold off for now |  | add finishing touches to screen sizing and placement
2023-02-20 | 1.5hr | documentation | documenting time from this week | Trying to decide if I'll keep current location function | continue onto Yelp implementation
Goals: Get planned APIs onto page, functioning in its proper way Challenges: Getting that geocoding to get current location causes issues that keep retreiving the location
Week 5
2023-02-21 | 1.5hr | coding | did some clean up on css and commited a push |  | Meet with supervisor
2023-02-22 | 1.5hr | supervisor meeting | Great news! He likes the design so far and now wants to see real data. Wants to see map functionality with real places and google map searches |  | Switch code from a static to dynamic look
2023-02-23 | 3hr | research | Reseacrhed more info to come from map data and found features to implement. Looked at examples and different ways to exhibit data |  | Work towards having features apart of project
2023-02-24 | 2hr | coding | worked towards making code modular, creating objects to hold data from API search | Figuring out which object properties i could pull from results and saving them to object. Properties not saving to object outside function | devise plan to fix data not being passed
2023-02-25 | 1.5hr | research | Watched Youtube videos and used google to search why object data wouldn't save. Figured out i wasn't returning it outside the function | How am I goong to save the data ?
2023-02-26 | 2hr | coding | decided to keep data apart of function because of error google.map not found while outside of the init function. Ran into issue getting photo of place from results | Getting the proper query for pictures wasn't working. Desire was to geet array of photos of a singular place | tackle photos issue on actual google results
2023-02-27 | 1hr | coding | was able to pull data from results and put into activities list using its property name and creating elements interacting with the DOM
Goals: To get the infromation from the google map results and be able to interact with them. Challenges: Getting the data outside of the init method was not useable without return, I had to figure out how I'd place the data into an object
Week 6
2023-02-28 | 2hr | coding | edite css to support need for lots of info. Edited list sizing and carousel appearance on the page |  | Clean up code
2023-03-01 | 5hr | coding | removed html images and text placeholders and ran code to display google information | makingn sure parent nodes were assigned the right child in the right order was trial and error
2023-03-02 | 2hr | coding | implemented second search request to simulate multiple searches. | it proved to work so i commented it out for the mean time | figure out how to get multiple locations off a search
2023-03-03 | 2hr | research | wanted more search results and discovered nearby places search but that it would cost money |  | Talk with supervisor about costs
2023-03-04
2023-03-05 | 2hr | supervisor meeting | Talked about progress in getting infomration from google onto page and problem with money. Decided to stay on the free route until time to implement multple search query | Is it worth it spending the money?
2023-03-06 | 3hr | research/coidng | figured out functions involving maps had to be within Init function and moved everything inside. Commiteed another push to GitHub |  | Focus now on Yelp API
Goals: Simulate a search that retreives multiple locations and markers onto the map and lists Challenges: Ran into the road block of money. Had to determine whether I would be spending money to run this project or not.
Week 7
2023-03-07 | 4hr | research/coding | Found a Yelp API work through using Codecademy and began walk through | the walkthrough is said to potentially take days | Continue on journey with Codecademy
2023-03-08 | 6hr | research/coding | worked through whole Codecademy Yelp API walk through and am ready to implement it onto my own web page | The walkthrough prefromed its work through JSX so good idea as a means to turning project into potential React App | Implement Yelp onto page
2023-03-09 | 5hr | coding/css | GOT YELP API ON PAGE! Had to create elements through interacting with DOM to come up with images on screen. Saw that page wasn't aligning right so i had to implement grid layout and manually align items using grid areas. Had to remove current location button. | images were of varying sizes and looked crazy! Figuring out how to use grid for the first time came with difficulties like the dot operator acting as a place holder saved so many issues from arising. | figure out how to make images look nice on page
2023-03-10
2023-03-11 | 2hr | css | commented out Yelp API and got images to play with to properly format pictures and information of retaurants onto page | grid areas are cool and easy to work with so…More Grids!
2023-03-12
2023-03-13
Goals: Configure Yelp API onto page and display results in a pleasing way. Challenges: Had to figure out how to use grid layout and perform css i never got into learning before
Week 8
2023-03-14 | 1hr | coding | Touched up a biit more on grid alignment, sizing, and website UX design. Committed push onto GitHub
2023-03-15 | 2hr | research | Met up with AJ who brought insite to my project. In order for Yelp to work I needed to use heoku corsanywhere but if I could make my own server to make a request with, I'll eliminate the need for them. | I don't remember how to use Express! | Catch up on express servers and learn how heroku cors requests info from Yelp
2023-03-16
2023-03-17 | 2hr | research | Looked up videos of basics of express servers |  | decide how we're gonna add our own server
2023-03-18
2023-03-19
2023-03-20 | 1.5hr | coding | added some more stock photos to represent accurate amount of data and added css |  | meet with supervisor
Goals: Expand upon express server idea and continue in using mock data for the page. Challenges: Refershing my knowledge on Express was a bit of a challenge that still needs to be worked upon
Week 9
2023-03-21 | 2.5hr | meeting | met with supervisor who liked content. Discussed css styling for Yelp results. He hated empty space of page so i had to fill in blanks | adding css to all photos in the grid to make them fit was a bit challenging but do able | test idea to display content images
2023-03-22 | 1hr | coding/research | found nice way to display images so i had to learn the css to display that | the data needed more formattin so more work to be done
2023-03-23 | 3hr | coding/research | tried various ways to present data properly but there wasn't one clear way so i resulted to an embedded grid within another grid | the data seems static but it works, grids are a bit strange to understand fully but successful
2023-03-24
2023-03-25 | 1.5hr | testing | copied more data to mimic full pages of data to ensure proper functionality |  | successful testing, moving towards sing real search results
2023-03-26
2023-03-27
Goals: Needed to fall upon final design of Yelp results and make sure of consistency with data Challenges: Creating a blurred background for the image of the restaurant was a cool idea but dove into css i had to learn such as element positioning and z index
Week 10
2023-03-28
2023-03-29 | 1hr | meeting | reviewed with supervisor and got an approved push to GitHub
2023-03-30 | 5hr | back work | MAJOR DISCOVERY! I realized that my css only works for large screens! I spent lots of time editing css to imlement good look for tablet sized screens | i'm going to have to do this again for all major screen sizes | work on express server idea
2023-03-31 | 2hr | implementation | watched videos and implemented basic express server, experimenting with app.use and .get functions |  | learn how heroku gets data from Yelp
2023-04-01 | 2hr | research | figured because i got a cors error, i needed a specific cors avoidance code from npm, downloaded it and found it wasn't too helpful really.
2023-04-02 | 4hr | coding | i figured that it was a simple get reguest made so i had to research how to send get request and once achieved have to get it to the main js file. Issue was, I needed to pass along a header which contained my apikey but when researching i learned to use axios so i attempted that; had to learn the syntax and how to retrieve data and finally was able to pull data onto my server. | going back to relearn express was a bit much already but having to discover how to use axios now was a handful. Thankfully i know how to use npm and could easily access these resources | get data from server to main file
2023-04-03
Goals: Get a fairly simple/minimal express server running Challenges: Understanding how to make a request along with my passed header apikey didn't make much sense at all. There was some coode I didn't understand and desire to find something more simple.
SPRING BREAK
2023-04-04
2023-04-05 | 2hr | coding | try to export data but got error 'require is not defined' as a way to use express on main page | not only did require not work for express but also other imports i tried to make | research why im having problems
2023-04-06
2023-04-07
2023-04-08 | 1.5hr | research | figured the scripts needed modular type so i changed it and needed to do modular exports but still no joy | maybe the require function is a problem?
2023-04-09
2023-04-10 | 1hr | research | tried to used import instead of require | got type error that failed to resolve express
2023-04-11
2023-04-12 | 8 hours of research trial and error. No luck with importing
2023-04-13
2023-04-14
2023-04-15
2023-04-16
2023-04-17
2023-04-18
2023-04-19
2023-04-20
Week 11
2023-04-21 | 1.5hr | coding | made test file to start from scratch to implement import and require methods to use express. I followed the tutorials to the tea and couldn't get it to work | I need help! I'll speak to my cs classmates | meet with a classmate for assistance
2023-04-22 | 2hr | team work | worked with a peer to try and find the error. We made edits, examined the code and other people's code still no joy. We faulted to restarting the dependancies and json files and start a fresh | starting over is painful… Not even working with a mate could help to find the solution | restart the files i have
2023-04-23 | 6hr | coding | restarted in my coding and still had same error result… I did discover that i can instead get the HTML and CSS onto the server side using sendFile method but had troubles having the css apply to the html that was transferred over. I looked up videos and found a common error made by people which resulted in me changing my file system layout but still errors. | there's a whole lot of errors now i'm running into in trying to get this server ran so i can work my site independantly
2023-04-24 | 3hr | coding | tried different work arounds with the server side of the page and defaulted to just sending over the Yelp data but still couldn't require or import so i reverted back to heroku and pushed | Not sure if I could work server side into this project at its current state but will attempt in the future | continue the grind
2023-04-25 | 4hr | coding | decided to test out with real data from map snd used the paid portion of code to pull multiple data onto page. Began to implement footer back into page but can't get it to stick to the bottom on the large screen but the small screen works fine. Update css based on a user run test and their feedback. Commited another push
2023-04-26 | 3hr | coding | put halt to pulling map data because of money. Implemented search bar for manual searching of locations for yelp api. Added a list of almost every city in the world to implement auto fill section of search bar | fitting the search bar onto the page and making adjustments to the wole page took its time but was successful. Had to use awk to parse file to get the data i wanted then format it to have the commas in order to fit into an array
2023-04-27 | 3hr | coding | implemented more search options to specify food search on Yelp. Also took the liberty to separate js files for easier readability | accessing data from a specified file was difficult because of import issue so had to make consious decisions on what file controlled what data
Goals: Challenges:
Week 12
2023-04-28 | 2.5hr | coding | implement function to pull search from input and dynamically produce Yelp data. Got datta ti be presented once the user hits enter key on tge search bar. Also implemented error catching code which fixed the problem of page not presenting all photos from google maps api nearby search | found that error catching code causes less breaks in the program and allows for smoother sailing. Had trouble making sure the form didn't submit when presseinng enter key. | move functinoality to apply to map as well
2023-04-29 | 3hr | coding | made functionality of dynamic search apply to the map, changing the initial query search results to the new one typed in by search. Pictures and attraction name within lists are dynamically changed as well. Committed two pushes to GitHub. |  | figure out how to set map poosition dynamically
2023-04-30 | 5hr | coding | made init function more modular by placing into separate functions for nearby search and query search. Added comments to page to add readability and began to work on setting map to search result. Needed to use Geocoding on google maps but was not authenticated so i had to contact customer support and we fixed the issue. Afterwards, I used geocoding to turn the name search into a longitude latitude search and apply that to the map which moved it to thhe location searched for and presented new attraction list with names. re-implemented current location and committed two psuhes | Having to talk to customer support was new for me and it shows me the drive i turly have for this and the community that's there to help in problems. Found issues with current location being called multiple times on key inputs on page. | touch up on minor errors
2023-05-01 | 2.5hr | researched | researched cause of multiple calls of current location and found a way to stop the location searching |  | apply newly found code
2023-05-02 | 1hr | coding | applied change to code to fix error with current location, committed a push | Problem was fixed for a good couple of minutes and then the location was called again by itself... | Gotta figure out how to fix it again
2023-05-03 | 3.5hr | coding | began applying css for responsive design across all screen sizes. Also made a work around on location by not having it change map loaction and making boolean to have it occur once though the problem still lies where it calls by itself | the footer is a big problem for me. I may have to hardoode a placement of the footer so page is satisficable (learned that word in CISC HCI!)
2023-05-04
Goals: Challenges:
Week 13
2023-05-05 | 2hr | documentation | began to shift documentation from word to excel
2023-05-06 | 8hr finishing up cathinf up data onto excel
2023-05-07
2023-05-08 |  |  | Removed old files and pushed the new log
2023-05-09 | 6hr Preparing documentation for presentation
2023-05-10
2023-05-11
Goals: Challenges:
Week 14
2023-05-12
2023-05-13
2023-05-14
2023-05-15
2023-05-16